## Slide 1: Tennessee K of C Ceremonials 2016
Thanks for Continuous Improvement!

## Slide 2: Outline
2015 Highlights – Lessons Learned
What can be done to improve?
2016 Schedule – Policies, planning, execution
Responsibilities - GKs, DDs, Teams, Officers
Emphasis Areas – Scheduling, Protocol
Questions - Answers

## Slide 3: 2015 Highlights & Lessons Learned
Ten Knighthood Degrees in past fraternal year
  Highlights - Excellent team prep, DD/GK/Team Communication, improving coordination
  LL -Scheduling must be solid at least one month in advance to support State, Supreme and long distance travelers
State policy – post Knighthood degree dates and locations six months in advance; confirm times six weeks in advance
  State calendar updated; will send out email queries to confirm dates, times and readiness

## Slide 4: What Can Be Done to Improve?
DD Inputs Needed
  1) ?
  2) ?
  3) ?

## Slide 5: 2016 – 2017 Knighthood and Patriotic Ceremonials Planning Calendar
Region | Date | District Deputy | Team Capt | Host Council / Location | Patriotic Degree Schedule Supported
West - Memphis | 20 Aug 16 | D Zwissler | M Rominiski | Memphis | 17 Sep 2016 Memphis
Mid - Nashville | 27 Aug 16 | F Pierce | M Wiedemer | 3537 Clarksville | 5 Nov 2016 Clarksville
East – Chatt | 24 Sept 16 | E Pelton | T Staller/M Wills | 6099 Chattano | 13 May 2017 Chattanooga
East - Cookev | 15 Oct 16 | P Keller | T Staller/M Wills | Cookeville | 22 Apr 2017 Lenoir City
Mid - Nashville | 23 Oct 16 | A Stanley | Mike Wiedemer | Smyrna | 5 Nov 2016 Clarksville
East - Knoxville | 12 Nov 16 | D Brown | T Staller/M Wills | Knoxville | 22 Apr 2017 Lenoir City
Mid - Nashville | 3 Dec 16 | J Finke | M Wiedemer | 3991 Tullahom | 11 Mar 2017 Murfreesboro
West - Memphis | 21 Jan 17 | D Zwissler | M Rominski |  | TBD
Mid - Nashville | 28 Jan 17 | J Woods | M Wiedemer | 15234 Brentwo | 11 Mar 2017 Murfreesboro
East - Knoxville | X Feb 17 | TBD | T Staller/M Wills | TBD | 22 Apr 2017 Lenoir City
East - Chatt | X Mar 17 | TBD | T Staller/M Wills | TBD | 13 May 2017 Chattanooga

## Slide 6: Responsibilities / Goals / Thresholds
GKs Responsibilities: Schedule, coordinate candidates for Admission degree ceremonies. Form Admission degree teams. Goal: Schedule, coordinate Admission degrees monthly; Cancel as necessary. Threshold: Candidates to monthly Admission degree in district.
DD Responsibilities: Certify Admission degree teams; form Formation degree teams; schedule, coordinate Formation degrees; Goal: Monthly Formation degrees in district. Threshold: Formation degree ceremony in district every quarter.

## Slide 7: Responsibilities / Goals / Thresholds (cont’d)
Ceremonial Director Responsibilities: Form Knighthood degree teams; schedule, coordinate Knighthood degrees. Goal: Monthly Knighthood degree ceremonies. Threshold: Ten Knighthood degrees per year to support five annual Patriotic degree ceremonies.
State Deputy Responsibilities: Certify Formation and Knighthood degree teams; attend Knighthood and Patriotic degree ceremonies.
State District Master Responsibilities: Certify Patriotic degree teams/members; schedule, coordinate and lead Patriotic degree ceremonies.

## Slide 8: 2016 Look Ahead/Emphasis
Scheduling – Communicate and coordinate! Complete tentative Knighthood degree schedule today! Place Formation degree dates on State website!!
Patriotic Degree schedule: 2016 – Firm - Sep 17 (Memphis); Nov 5 (Murfreesboro). 2017 – Mar 11 (East); Mar 4 (West); Mar 11 (Middle); Apr 22 (East); May 13 (Middle).
Middle Tennessee Patriotic degree team needs a volunteer for one position. Sir Knights see Mike Porter or Mike Wiedemer to join the team!!!
Dress for the event: Patriotic Degree - Tux for candidates, team and observers. Knighthood Degree – Coat and Tie for candidates, team and observers.

## Slide 9: 2016 Look Ahead/Emphasis (cont’d)
MEMBERSHIP ADMISSION DEGREE – Schedule an Admission degree associated with your October 2016 recruitment initiative. Here is a potential pitch.
“Men of our parish, what can you do to help our Christian brothers suffering persecution at the hands of ISIS?" What can you do to help defeat ISIS, the enemy of our country and our religion? What can you do in the Volunteer State to support these worthy causes? Who can you turn to?" The Knights of Columbus! Did you know that the Knights of Columbus is leading humanitarian relief efforts for persecuted Christians in the Middle East? Did you know that the Knights of Columbus led the effort to get the U.S. State Department to officially declare the extermination of Christians in the Middle East as genocide. Did you know that the volunteer State of Tennessee has almost 12,000 knights already in the fight and ready to stand at your side? If you are a man, 18 years of age or older and a practicing Catholic, join us in the fight for our Christian brothers and religious freedom. Ask a Knight how you can join, today!
Protocol – Remember your Admission degree lessons? Remember your Formation degree lessons? Remember, remind, redo!

## Slide 10: Questions?
Now…….
Later……Mike Wiedemer 931 308-1923; wiedemerm@gmail.com